## Robeasca
| #VALUE! |  | H Herastrau Park, Str. Ghetarilor 23-25
et.4 Sector 1, 014106, Bucuresti
Contact: +40 31 005 1520
office@hagagenergy.com
www,hagagenergy.com
LISTA LUCRARILOR , CANTITATILE PROPUSE spre EXECUTIE aferente PROIECTULUI
Infiintarea distributie de gaze naturale in comuna BUTURUGENI, judet GIURGIU
Nr. | Cod activitate | Activitate Interna | Um | Cant. Activitate | Val.Mat | Val.Srv | Val.TOTALA
1 |  | CAMIN VANE 1.5X1.5M PREF INSTALATII GAZE NL_HDF | Buc | 1 |  |  | 0
2 |  | CONDUCTA BRANSAMENT GAZ DN.32 MONTATA INCLUSIV MANOPERA SUDURI NL_HDF | m | 2.4 |  |  | 0
3 |  | CONDUCTA GAZ DN.180 MONTATA INCLUSIV MANOPERA SUDURI NL_HDF | m | 110 |  |  | 0
4 |  | CONDUCTA GAZ DN.250 MONTATA INCLUSIV MANOPERA SUDURI NL_HDF | m | 3962 |  |  | 0
5 |  | DESFACERE ASFALT LA MP NL_HDF | mp | 24 |  |  | 0
6 |  | DESFACERE BALAST LA MP NL_HDF | mp | 59 |  |  | 0
7 |  | DESFACERE BETON la MP NL_HDF | mp | 616 |  |  | 0
8 |  | FORAJ ORIZONTAL DN= 350MM / 14" (fara conduca de protectie) NL_HDF | Buc | 10 |  |  | 0
9 |  | MONTAJ BRANSAMENT 250x32 (HIDRAULICA - TEU BRANSAMENT 250x32, MUFE DE32, REISER DE32, ROBINET 1”) N | Buc | 1 |  |  | 0
10 |  | MONTARE RASUFLATOARE CU CAPAC (include rasuflatoare) NL_HDF | Buc | 2 |  |  | 0
11 |  | MONTARE RASUFLATOARE FARA CAPAC (include rasuflatoare) NL_HDF | Buc | 291 |  |  | 0
12 |  | PROBA DE REZISTENTA(Valoare incl in Mnt CND) CONDUCTA DN.32/63 BRNSMNT GAZ NL_HDF | Buc | 1 | Inclus in conducta | Inclus in conducta | Inclus in conducta
13 |  | PROBA DE REZISTENTA(Valoare incl in Mnt CND) CONDUCTA GAZ DN.180 NL_HDF | Buc | 2 | Inclus in conducta | Inclus in conducta | Inclus in conducta
14 |  | PROBA DE REZISTENTA(Valoare incl in Mnt CND) CONDUCTA GAZ DN.250 NL_HDF | Buc | 19 | Inclus in conducta | Inclus in conducta | Inclus in conducta
15 |  | PROBA PRELIMINARA(Valoare incl in Mnt CND) CONDUCTA DN.32/63 BRNSMNT GAZ NL_HDF | Buc | 1 | Inclus in conducta | Inclus in conducta | Inclus in conducta
16 |  | PROBA PRELIMINARA(Valoare incl in Mnt CND) CONDUCTA GAZ DN.180 NL_HDF | Buc | 2 | Inclus in conducta | Inclus in conducta | Inclus in conducta
17 |  | PROBA PRELIMINARA(Valoare incl in Mnt CND) CONDUCTA GAZ DN.250 NL_HDF | Buc | 19 | Inclus in conducta | Inclus in conducta | Inclus in conducta
18 |  | REFACERE ASFALT LA MP NL_HDF | mp | 24 |  |  | 0
19 |  | REFACERE BALAST LA MP NL_HDF | mp | 59 |  |  | 0
20 |  | REFACERE BETON la MP NL_HDF | mp | 616 |  |  | 0
21 |  | RETEA AERIANA D=150mm - SUDURA FITINGURI TRANZITIE DIAM 180/6" - NL_HDF | Buc | 3 |  |  | 0
22 |  | RETEA AERIANA D=150mm/6" - COT otel 90gr d=6" GATA CONF MONTAT PE CND PANA LA 3M ADANCIME DN 150 NL | Buc | 2 |  |  | 0
23 |  | SUBTR FORAJ - MONTAJ TUB PROTECTIE,TEAVA OTEL 14" D=356mm TRAV. DE DRM PTR. PROT CONDUCTEI NL HDF | m | 11 |  |  | 0
24 |  | SUBTR SANT DESCH - MONTAJ TUB PROTECTIE D=315mm PVC SN8 MON IN SANT LA TRAV. DE DRM PTR. PROTECTIA C | m | 20 |  |  | 0
25 |  | SUBTR SANT DESCH - MONTAJ TUB PROTECTIE D=355mm PE100 SDR17 MON IN SANT LA TRAV. DE DRM PTR. PROTECT | m | 144 |  |  | 0
26 |  | SUBTR SANT DESCH - MONTAJ TUB PROTECTIE D=400mm PVC SN8 MON IN SANT LA TRAV. DE DRM PTR. PROTECTIA C | m | 743 |  |  | 0
27 |  | Sudura cap la cap (doar fiting) COT 90gr D=250mm fiting gaz PE100 SDR11 NL_HDF | Buc | 3 |  |  | 0
28 |  | Sudura cap la cap (doar fiting) TEU EGAL D=250mm fiting gaz PEHD PE100 SDR11 NL_HDF | Buc | 1 |  |  | 0
29 |  | Sudura cap la cap (doar fiting) TEU REDUS D=250/110mm fiting gaz PEHD PE100 SDR11 NL_HDF | Buc | 14 |  |  | 0
30 |  | Sudura EF (doar fiting) DOP D=180mm electrosudabil gaz,PEHD NL_HDF | Buc | 1 |  |  | 0
31 |  | Sudura EF (doar fiting) DOP D=250mm electrosudabil gaz,PEHD NL_HDF | Buc | 1 |  |  | 0
32 |  | Sudura EF (doar fiting) MUFA D=250mm electrosudabila gaz,PEHD NL_HDF | Buc | 10 |  |  | 0
33 |  | Sudura EF (doar fiting) REDUCTIE D=110/63mm electrosudabila gaz,PEHD NL_HDF | Buc | 14 |  |  | 0
34 |  | Sudura EF (doar fiting) REDUCTIE D=250/180mm electrosudabila gaz,PEHD NL_HDF | Buc | 1 |  |  | 0
35 |  | Sudura EF (doar fiting) TEU EGAL D=180mm electrosudabil gaz,PEHD NL_HDF | Buc | 1 |  |  | 0
36 |  | VANA DN.250 - ROBINET PE CU CAPETE SUDURA PT. INSTALATII DE GAZE (include manopera) NL_HDF | Buc | 2 |  |  | 0
37 |  | VANA ol 6" - ROBINET OTEL PT. INSTALATII DE GAZE (include manopera) NL_HDF | Buc | 2 |  |  | 0
38 |  | VANA ol 6" - ROBINET OTEL PT. INSTALATII DE GAZE IN CAMINDE BETON (include manopera) NL_HDF | Buc | 1 |  |  | 0
TOTAL OFERTA FARA TVA | [6 empty] | 0
| Oferta include: | Managementul Proiectului
* SEF DE SANTIER AUTORIZAT
*RESPONSABIL TEHNIC CU EXECUTIA
* CONTROLUL CALITATII
* RSSM - Responsabil Sanatate si Securitate in Munca
* Alte reglementari legale
Intocmirea intregii documentatii aferente Cartii Tehnice a Constructiei ( Se va preda la fiecare Situatie de Lucrari propuse spre decontare)
Intocmirea documentatiei specifice de Securitate si Sanatate in Munca (SSM), inclusiv planul de prevenire si protectie si instructiunile proprii, conform prevederilor Legale, aplicabile pe durata executiei lucrarilor.
Intocmirea documentatiei si implementarea masurileo de management al traficului, conform cerintelor legale si specifice proiectului, incusiv costurile aferente.
* PUNCTAJ MAXIM ACORDAT: 50p